## Initial Plan
Color Coding |  | Completed |  |  |  | FALL 2022 SEMESTER
In Progress
[5 empty] | Week # | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[5 empty] | Date | 2022-09-13 | 2022-09-20 | 2022-09-27 | 2022-10-11 | 2022-10-18 | 2022-10-25 | 2022-11-01 | 2022-11-08 | 2022-11-15 | 2022-11-22 | 2022-11-29 | 2022-12-06 | 2022-12-13 | 2022-12-20 | 2018-05-08
Project Phase | Activity | Task Owner Name | Start Date | End Date | Progress %
Project Initiation | Discuss project proposals | ALL | 2022-09-13 | 2022-09-13 | 0%
| Confirm Project Team Roles | ALL | 2022-09-13 | 2022-09-13 | 0%
| Develop two business cases | ALL | 2022-09-13 | 2022-09-13 | 0%
| Develop Project Initiation Document (PID) | Zubair | 2022-09-20 | 2022-09-27 | 0%
| Produce initial Project Plan, RACI | Zubair | 2022-09-27 | 2022-10-11 | 0%
MILESTONE 1: INITIAL PROJECT PLAN COMPLETED
Requirements Definition | Produce BRM diagram, define User Roles | Gayathri | 2022-10-11 | 2022-10-18 | 0%
| Produce Context Diagram, Define System Interfaces | Divyaa | 2022-10-11 | 2022-10-18 | 0%
| Define Business Requirements | Chithra | 2022-10-18 | 2022-10-25 | 0%
| Agree to System Requirements types | All | 2022-10-25 | 2022-11-01 | 0%
| Define Functional Decomposition | All | 2022-10-25 | 2022-11-01 | 0%
| Produce RCT document | Chithra | 2022-10-25 | 2022-11-01 | 0%
| Decide which features to implement this semester | All | 2022-11-01 | 2022-11-08 | 0%
| Produce analysis diagrams (UML, DFD) | Chithra | 2022-11-01 | 2022-11-08 | 0%
| Define functional requirements (User Stories) | Divyaa | 2022-11-01 | 2022-11-08 | 0%
| Update Project Plan with additional requirements tasks | All | 2022-11-01 | 2022-11-08 | 0%
MILESTONE 2: REQUIREMENTS COMPLETED
Design | Architecture design (2 diagrams) | Divyaa | 2022-11-08 | 2022-11-15 | 0%
| Database Design (ERD, Table spec) | Somyadip | 2022-11-08 | 2022-11-15 | 0%
| System Interface Design | Divyaa | 2022-11-08 | 2022-11-15 | 0%
| User interface design | Divyaa | 2022-11-08 | 2022-11-15 | 0%
MILESTONE 3: DESIGN COMPLETED
Code | Functionality Detailed Design | Divyaa | 2022-11-15 | 2022-11-22 | 0%
| Establish code repository in GitHUb | Divyaa | 2022-11-15 | 2022-11-22 | 0%
| Coding & Implemenation | Somyadip | 2022-11-15 | 2022-11-22 | 0%
MILESTONE 4: CODING COMPLETED
Integration & Testing | Plan testing, produce a Test Plan document | Rob | 2022-11-22 | 2022-11-29 | 0%
| Evaluate Features to be Tested | Rob | 2022-11-22 | 2022-11-29 | 0%
| Design Test Cases | Rob | 2022-11-29 | 2022-12-06 | 0%
| Execute Test Cases | Rob | 2022-11-29 | 2022-12-06 | 0%
| Anaylze Test Results | ALL | 2022-11-29 | 2022-12-10 | 0%
MILESTONE 5: TESTING COMPLETED
Project Presentation | Prepare Application Demo for the Presentation | ALL | 2022-12-13 | 2022-12-20 | 0%

## Final Plan
Color Coding |  |  | Completed |  |  |  | FALL 2022 SEMESTER
In Progress
[6 empty] | Week # | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[6 empty] | Date | 2022-09-13 | 2022-09-20 | 2022-09-27 | 2022-10-11 | 2022-10-18 | 2022-10-25 | 2022-11-01 | 2022-11-08 | 2022-11-15 | 2022-11-22 | 2022-11-29 | 2022-12-06 | 2022-12-13 | 2022-12-20 | 2018-05-08
Project Phase | Activity |  | Task Owner Name | Start Date | End Date | Progress %
Project Initiation | Discuss project proposals |  | ALL | 2022-09-13 | 2022-09-13 | 100%
| Confirm Project Team Roles |  | ALL | 2022-09-13 | 2022-09-13 | 100%
| Develop two business cases |  | ALL | 2022-09-13 | 2022-09-20 | 100%
| Develop Project Initiation Document (PID) |  | Zubair | 2022-09-20 | 2022-09-27 | 100%
| Produce initial Project Plan, RACI |  | Zubair | 2022-09-27 | 2022-10-11 | 100%
MILESTONE 1: INITIAL PROJECT PLAN COMPLETED
Requirements Definition | Produce BRM diagram, define User Roles |  | Gayathri | 2022-10-11 | 2022-10-18 | 100%
| Produce Context Diagram, Define System Interfaces |  | Divyaa | 2022-10-11 | 2022-10-18 | 100%
| Define Business Requirements |  | Chitra | 2022-10-18 | 2022-10-25 | 100%
| Agree to System Requirements types |  | All | 2022-10-18 | 2022-10-25 | 100%
| Define Functional Decomposition |  | All | 2022-10-18 | 2022-10-25 | 100%
| Produce RCT document |  | Chitra | 2022-10-18 | 2022-10-25 | 100%
| Decide which features to implement this semester |  | All | 2022-10-25 | 2022-11-01 | 100%
| Produce analysis diagrams (UML, DFD) |  | Chitra | 2022-10-25 | 2022-11-01 | 100%
| Define functional requirements (User Stories) |  | Divyaa | 2022-10-25 | 2022-11-01 | 100%
| Update Project Plan with additional requirements tasks |  | All | 2022-10-25 | 2022-11-01 | 100%
MILESTONE 2: REQUIREMENTS COMPLETED
Design | Architecture design (2 diagrams) |  | Divyaa | 2022-11-15 | 2022-11-22 | 100%
| Database Design (ERD, Table spec) |  | Soumyadip | 2022-11-15 | 2022-11-22 | 100%
| System Interface Design |  | Divyaa | 2022-11-22 | 2022-11-29 | 100%
| User interface design |  | Divyaa | 2022-11-22 | 2022-11-29 | 100%
MILESTONE 3: DESIGN COMPLETED
Code | Scan QR | Functionality Design | Divyaa | 2022-11-22 | 2022-11-29 | 100%
|  | Coding | Soumyadip | 2022-11-22 | 2022-11-29 | 100%
| Create an Account | Functionality Design | Divyaa | 2022-11-22 | 2022-11-29 | 100%
|  | Coding | Soumyadip | 2022-11-22 | 2022-11-29 | 100%
| Sign into Account | Functionality Design | Divyaa | 2022-11-22 | 2022-11-29 | 100%
|  | Coding | Soumyadip | 2022-11-22 | 2022-11-29 | 100%
| Modify user's Information | Functionality Design | Divyaa | 2022-11-22 | 2022-11-29 | 100%
|  | Coding | Soumyadip | 2022-11-22 | 2022-11-29 | 100%
| Delete an Account | Functionality Design | Divyaa | 2022-11-22 | 2022-11-29 | 100%
|  | Coding | Soumyadip | 2022-11-22 | 2022-11-29 | 100%
MILESTONE 4: CODING COMPLETED
Integration & Testing | Plan testing, produce a Test Plan document |  | Rob | 2022-11-29 | 2022-12-06 | 0%
| Evaluate Features to be Tested |  | ALL | 2022-11-29 | 2022-12-06 | 0%
| Scan QR | Design Test Cases | Rob | 2022-11-29 | 2022-12-06 | 0%
|  | Execute Test Cases | Rob | 2022-11-29 | 2022-12-06 | 0%
|  | Anaylze Test Results | ALL | 2022-11-29 | 2022-12-06 | 0%
| Create an Account | Design Test Cases | Rob | 2022-11-29 | 2022-12-06 | 0%
|  | Execute Test Cases | Rob | 2022-11-29 | 2022-12-06 | 0%
|  | Anaylze Test Results | ALL | 2022-11-29 | 2022-12-06 | 0%
| Sign into Account | Design Test Cases | Rob | 2022-12-06 | 2022-12-10 | 0%
|  | Execute Test Cases | Rob | 2022-12-06 | 2022-12-10 | 0%
|  | Anaylze Test Results | ALL | 2022-12-06 | 2022-12-10 | 0%
| Modify user's Information | Design Test Cases | Rob | 2022-12-06 | 2022-12-10 | 0%
|  | Execute Test Cases | Rob | 2022-12-06 | 2022-12-10 | 0%
|  | Anaylze Test Results | ALL | 2022-12-06 | 2022-12-10 | 0%
| Delete an Account | Design Test Cases | Rob | 2022-12-06 | 2022-12-10 | 0%
|  | Execute Test Cases | Rob | 2022-12-06 | 2022-12-10 | 0%
|  | Anaylze Test Results | ALL | 2022-12-06 | 2022-12-10 | 0%
MILESTONE 5: TESTING COMPLETED
Project Presentation | Prepare Application Demo for the Presentation |  | ALL | 2022-12-13 | 2022-12-20 | 0%