## ROADMAP
QR Yummy Application
|  |  | Release 1 |  | Release 2
Application Modules | Feature Backlog | Story Points | Iteration 1 - 3/3/23 | Iteration 2 - 3/31/23 | Iteration 3 - 4/21/23 | Iteration 4 - 5/12/23
Module 1 - Advertising | 01.01 Scan QR
| 01.02 View First time user deals | 3 |  |  | X
| 01.03 View member deals | 3 |  |  | X
| 01.04 View Occasional deals | 3 |  |  | X
Module 2 - User's Account | 02.01 Create an Account
02.02 Sign into Account
02.03 Modify user's Information
| 02.04 Review previous orders | 3 | X
| 02.05 Reserving Table | 3 |  |  |  | X
| 02.06 Add a payment method | 4 |  | X
| 02.07 Contact a Customer Support | 3 |  |  |  | X
02.08 Delete an Account
Module 3 - Browse for menu | 03.01 Selecting Menu | 3 | X
| 03.02 Selecting Cuisine | 3 | X
| 03.03 Rating the food | 3 |  |  |  | X
Module 4 - Cart | 04.01 Add order | 3 | X
| 04.02 Add multiple Orders | 3 |  |  | X
| 04.03 Make a Payment | 4 |  | X
| 04.04 Add money to wallet | 3 |  |  |  | X
| 04.05 Tip the waiter | 4 |  | X
|  | VELOCITY: | 12 | 12 | 12 | 12

## USERSTORY
Epics |  | QR Yummy - User Story Map
Epic 1 - Advertising |  | Epic 1 - Advertising | Epic 2 - User's Account | Epic 3 - Browse for menu | Epic 4 - Cart
Epic 2 - User's Account | User Stories |  | 02.04 Review previous orders | 03.01 Selecting Menu | 04.01 Add order
Epic 3 - Browse for menu |  |  |  | 03.02 Selecting Cuisine
Epic 4 - Cart | [5 empty] | Iteration 1
|  |  | 02.06 Add a payment method |  | 04.03 Make a Payment
04.05 Tip the waiter
Iteration 2
|  | 01.02 View First time user deals |  |  | 04.02 Add multiple Orders
01.03 View member deals
|  | 01.04 View Occasional deals |  |  |  | Iteration 3
|  |  | 02.05 Reserving Table | 03.03 Rating the food | 04.04 Add money to wallet
02.07 Contact a Customer Support
Iteration 4