## R1 I1
Task # | Iteration | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner
1 | R1 - I1 | 02. User's Account | 2.04 | Review Previous orders | Implement functionality to check the previous orders placed by the customer | 2023-03-01 | 2023-03-02 | 100% | Soumyadip Chatterjee
2 | R1 - I1 | 02. User's Account | 2.04 | Review Previous orders | Implement GUI by which they can check previous orders | 2023-03-01 | 2023-03-02 | 100% | Soumyadip Chatterjee
3 | R1 - I1 | 02. User's Account | 2.04 | Review Previous orders | Crosscut: Entitlements,Crosscut: Field Validation,user check the previous orders by authenticating the details | 2023-03-28 | 2023-03-28 | 100% | Soumyadip Chatterjee
4 | R1 - I1 | 02. User's Account | 2.04 | Review Previous orders | Crosscut: Data Dependency Validation,user check the previous orders based upon the past orders placed by the user | 2023-03-28 | 2023-03-28 | 100% | Soumyadip Chatterjee
5 | R1 - I1 | 02. User's Account | 2.04 | Review Previous orders | Check query ,which shows all the records stored in database | 2023-03-28 | 2023-03-28 | 100% | Soumyadip Chatterjee
6 | R1 - I1 | 02. User's Account | 2.04 | Review Previous orders | Create test cases to check the functionality | 2023-03-30 | 2023-03-30 | 100% | Soumyadip Chatterjee
7 | R1 - I1 | 02. User's Account | 2.04 | Review Previous orders | Execute test cases and document the test execution log | 2023-03-30 | 2023-03-30 | 100% | Soumyadip Chatterjee
8 | R1 - I1 | 03. Browse for Menu | 3.01 | Selecting Menu | Implement functionality to explore the menu options provide by the restaurant | 2023-02-20 | 2023-02-22 | 100% | Divya mohan kumar
9 | R1 - I1 | 03. Browse for Menu | 3.01 | Selecting Menu | Create the GUI where they can explore the menu | 2023-02-20 | 2023-02-22 | 100% | Divya mohan kumar
10 | R1 - I1 | 03. Browse for Menu | 3.01 | Selecting Menu | Crosscut: Entitlements,Crosscut: Data Dependency Validation | 2023-02-20 | 2023-02-22 | 100% | Divya mohan kumar
11 | R1 - I1 | 03. Browse for Menu | 3.01 | Selecting Menu | Crosscut: Connectivity,user explores the dishes provided by the restaurant | 2023-02-20 | 2023-02-22 | 100% | Divya mohan kumar
12 | R1 - I1 | 03. Browse for Menu | 3.01 | Selecting Menu | Create db query which stores all the menu items provided by the restaurant | 2023-02-20 | 2023-02-22 | 100% | Soumyadip Chatterjee
13 | R1 - I1 | 03. Browse for Menu | 3.01 | Selecting Menu | Create test cases to check the functionality | 2023-02-22 | 2023-02-22 | 100% | Divya mohan kumar
14 | R1 - I1 | 03. Browse for Menu | 3.01 | Selecting Menu | Execute test cases and document the test execution log | 2023-02-22 | 2023-02-22 | 100% | Divya mohan kumar
15 | R1 - I1 | 03. Browse for Menu | 3.02 | Selecting Cuisine | Implement functionality to explore the cuisine options provided by the restaurant | 2023-02-23 | 2023-02-25 | 100% | Divya mohan kumar
16 | R1 - I1 | 03. Browse for Menu | 3.02 | Selecting Cuisine | Create GUI where they can explore all cuisines available | 2023-02-23 | 2023-02-25 | 100% | Divya mohan kumar
17 | R1 - I1 | 03. Browse for Menu | 3.02 | Selecting Cuisine | Crosscut: Entitlement,Crosscut: Data Dependency Validation | 2023-02-23 | 2023-02-25 | 100% | Divya mohan kumar
18 | R1 - I1 | 03. Browse for Menu | 3.02 | Selecting Cuisine | Crosscut: Connectivity,Crosscut:Data Flow Out | 2023-02-23 | 2023-02-25 | 100% | Divya mohan kumar
19 | R1 - I1 | 03. Browse for Menu | 3.02 | Selecting Cuisine | Create a query which stores all the cuisines provided by the restaurant | 2023-02-23 | 2023-02-25 | 100% | Soumyadip Chatterjee
20 | R1 - I1 | 03. Browse for Menu | 3.02 | Selecting Cuisine | Create test cases for fuctionality | 2023-02-25 | 2023-02-25 | 100% | Divya mohan kumar
21 | R1 - I1 | 03. Browse for Menu | 3.02 | Selecting Cuisine | Execute test cases and document the test execution log | 2023-02-25 | 2023-02-25 | 100% | Divya mohan kumar
22 | R1 - I1 | 04. Cart | 4.01 | Add order | Implement functionality to add order to the cart, which is selection of the dish by the customer | 2023-02-26 | 2023-02-28 | 100% | Soumyadip Chatterjee
23 | R1 - I1 | 04. Cart | 4.01 | Add order | Create GUI where they can add the order to the cart | 2023-02-26 | 2023-02-28 | 100% | Soumyadip Chatterjee
24 | R1 - I1 | 04. Cart | 4.01 | Add order | Crosscut:Entitlement,Crosscut: Data driven defaults,user explores and select the dish by the function goes on | 2023-02-26 | 2023-02-28 | 100% | Soumyadip Chatterjee
25 | R1 - I1 | 04. Cart | 4.01 | Add order | Crosscut: Connectivity,Crosscut:Data Flow In,Crosscut: Data Flow Out | 2023-02-26 | 2023-02-28 | 100% | Soumyadip Chatterjee
26 | R1 - I1 | 04. Cart | 4.01 | Add order | Create a query which stores all the orders placed by the customers | 2023-02-26 | 2023-02-28 | 100% | Soumyadip Chatterjee
27 | R1 - I1 | 04. Cart | 4.01 | Add order | Create test cases for the functionality | 2023-02-28 | 2023-02-28 | 100% | Soumyadip Chatterjee
28 | R1 - I1 | 04. Cart | 4.01 | Add order | Execute test cases and document the test execution log | 2023-02-28 | 2023-02-28 | 100% | Soumyadip Chatterjee

## R1 I2
Task # | Iteration | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner
1 | R1 - I2 | 02. User's Account | 2.06 | Add a payment method | Implement functionality to add a payment method for the customer in order to place any order further | 2023-03-25 | 2023-03-25 | 100% | Soumyadip Chatterjee
2 | R1 - I2 | 02. User's Account | 2.06 | Add a payment method | Implement GUI by which they can explore the payment methods they have added | 2023-03-25 | 2023-03-25 | 100% | Soumyadip Chatterjee
3 | R1 - I2 | 02. User's Account | 2.06 | Add a payment method | Crosscut: Entitlements,Crosscut: Field Validation,user check the added payment methods by authenticating the details | 2023-03-26 | 2023-03-26 | 100% | Soumyadip Chatterjee
4 | R1 - I2 | 02. User's Account | 2.06 | Add a payment method | Crosscut: Data Dependency Validation,user check the added payment details | 2023-03-26 | 2023-03-26 | 100% | Soumyadip Chatterjee
5 | R1 - I2 | 02. User's Account | 2.06 | Add a payment method | Crosscut: Connectivity,user stored payment methods authenticating with database and banking technology ,Crosscut:Data Flow Out,stored user payment methods will be carried forward to make the payments when they order any dish | 2023-03-26 | 2023-03-26 | 100% | Soumyadip Chatterjee
6 | R1 - I2 | 02. User's Account | 2.06 | Add a payment method | Create a db query ,which stores the payment methods and a query to shows all the records stored in database | 2023-03-27 | 2023-03-27 | 100% | Soumyadip Chatterjee
7 | R1 - I2 | 02. User's Account | 2.06 | Add a payment method | Create test cases to check the functionality | 2023-03-30 | 2023-03-30 | 100% | Soumyadip Chatterjee
8 | R1 - I2 | 02. User's Account | 2.06 | Add a payment method | Execute test cases and document the test execution log | 2023-03-30 | 2023-03-30 | 100% | Soumyadip Chatterjee
9 | R1 - I2 | 04. Cart | 4.03 | Make a payment | Implement functionality to make a payment for the order placed | 2023-03-27 | 2023-03-27 | 100% | Soumyadip Chatterjee
10 | R1 - I2 | 04. Cart | 4.03 | Make a payment | Create the GUI where they can explore the payment panel | 2023-03-27 | 2023-03-27 | 100% | Soumyadip Chatterjee
11 | R1 - I2 | 04. Cart | 4.03 | Make a payment | Crosscut: Entitlements,Crosscut:Field Validation,Crosscut: Data Dependency Validation | 2023-03-28 | 2023-03-28 | 100% | Soumyadip Chatterjee
12 | R1 - I2 | 04. Cart | 4.03 | Make a payment | Crosscut: Data Flow In,Crosscut: Data Flow Out | 2023-03-28 | 2023-03-28 | 100% | Soumyadip Chatterjee
13 | R1 - I2 | 04. Cart | 4.03 | Make a payment | Create db query which stores the transaction records | 2023-03-28 | 2023-03-28 | 100% | Soumyadip Chatterjee
14 | R1 - I2 | 04. Cart | 4.03 | Make a payment | Create test cases to check the functionality | 2023-03-30 | 2023-03-30 | 100% | Soumyadip Chatterjee
15 | R1 - I2 | 04. Cart | 4.03 | Make a payment | Execute test cases and document the test execution log | 2023-03-30 | 2023-03-30 | 100% | Soumyadip Chatterjee
16 | R1 - I2 | 04. Cart | 4.05 | Tip the waiter | Implement functionality to tip the waiter as a appreciation of his/her service | 2023-03-28 | 2023-03-28 | 100% | Divya mohan kumar
17 | R1 - I2 | 04. Cart | 4.01 | Tip the waiter | Create GUI where they can enhance the option of tipping waiter | 2023-03-28 | 2023-03-28 | 100% | Divya mohan kumar
18 | R1 - I2 | 04. Cart | 4.01 | Tip the waiter | Crosscut: Entitlements,Crosscut:Field Validation,Crosscut: Data Dependency Validation | 2023-03-29 | 2023-03-29 | 100% | Divya mohan kumar
19 | R1 - I2 | 04. Cart | 4.01 | Tip the waiter | Crosscut: Calculations,Crosscut:Data Flow In,Crosscut: Data Flow Out | 2023-03-29 | 2023-03-29 | 100% | Divya mohan kumar
20 | R1 - I2 | 04. Cart | 4.01 | Tip the waiter | Create a query which stores records and transactions done for the waiter tips | 2023-03-29 | 2023-03-29 | 100% | Soumyadip Chatterjee
21 | R1 - I2 | 04. Cart | 4.01 | Tip the waiter | Create test cases for the functionality | 2023-03-30 | 2023-03-30 | 100% | Divya mohan kumar
22 | R1 - I2 | 04. Cart | 4.01 | Tip the waiter | Execute test cases and document the test execution log | 2023-03-30 | 2023-03-30 | 100% | Divya mohan kumar